## CarPlay Certification
Year |  |  | 2026 | [52 empty] | 2027
Week |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37
Date |  |  | 2026-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2027-09-13
Project Milestone
CarPlay | Function development | Function development | bar: 2026 W6 to 2026 W32
| Hardware Certification | USB IF & USB Signal Integrity | 2026 W45: Submit report & Approval
|  | USB IF & USB Signal Integrity | 2026 W45: Submit report & Approval
|  | WIFI | 2026 W45: Submit report & Approval
| Certification(1st) | Vehicle Available | bar: 2026 W35
|  | PPID | 2026 W6: Re-Submit; 2026 W8: Approval
|  | Submit CCR | 2026 W5: Submit; 2026 W9: Re-Submit; 2026 W13: Approval
|  | Submit CarPlay Integration Design - User Experience | 2026 W13: Submit; 2026 W21: Approval
|  | Submit CarPlay Integration Design - Graphics | 2026 W13: Submit; 2026 W21: Approval
Bench production(DT/HDCC) | bar: 2026 W1 to 2026 W9
|  | Video Decoder | 2026 W22: Test; 2026 W26: Submit report & Approval
Pre-Test | bar: 2026 W37 to 2026 W53
|  | USB performance | 2026 W41: Test; 2026 W44: Submit report & Approval
Bench shipment to CarPlay lab | bar: 2026 W51 to 2026 W52
|  | AuditTest | 2027 W1: Round 1; 2027 W3: Issue Fix; 2027 W6: Round 2
|  | ITUT & siri&esiri | 2026 W53: Submit report; 2027 W3: Approval
|  | Location Test & Wireless Performance | 2027 W1: pre test + Issue Fix; 2027 W6: Audit
|  | Vehicle Assessment | 2027 W9: Round 1; 2027 W11: Issue Fix; 2027 W14: Round 2
Exception Request | bar: 2027 W16 to 2027 W17
|  | Apple Final Review | 2027 W18: Approval
| Certification(2nd) | Vehicle Available | bar: 2026 W50
|  | USB IF & USB Signal Integrity | 2026 W45: Submit report & Approval
|  | PPID | 2026 W6: Re-Submit; 2026 W8: Approval
|  | Submit CCR | 2026 W13: Submit; 2026 W17: Approval
|  | Submit CarPlay Integration Design - User Experience | 2026 W18: Submit; 2026 W27: Approval
|  | Submit CarPlay Integration Design - Graphics | 2026 W18: Submit; 2026 W27: Approval
Bench production(Promaster/Fastback/Toro) | bar: 2026 W14 to 2026 W33
|  | Video Decoder | 2026 W28: Test; 2026 W32: Submit report & Approval
Pre-Test | bar: 2026 W51 to 2027 W15
|  | USB performance | 2027 W7: Test; 2027 W10: Submit report & Approval
Bench shipment to CarPlay lab | bar: 2027 W13 to 2027 W14
|  | AuditTest | 2027 W16: Round 1; 2027 W19: Issue Fix; 2027 W24: Round 2
|  | ITUT & siri&esiri | 2027 W7: Submit; 2027 W10: Approval
|  | Vehicle Assessment | 2027 W27: Round 1; 2027 W29: Issue Fix; 2027 W32: Round 2
Exception Request | bar: 2027 W34 to 2027 W35
|  | Apple Final Review | 2027 W36: Approval

## Android Auto Certification
Year |  |  | 2026 | [52 empty] | 2027
Week |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37
Date |  |  | 2026-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2027-09-13
Project Milestone
| Function development | Function development | bar: 2026 W6 to 2026 W32
| Certification(1st) | Vehicle Available | bar: 2026 W35
|  | Submit Application | 2026 W6: Submit; 2026 W15: Approval
Submit CERS
|  | Submit Project Specification | 2026 W18: Submit; 2026 W27: Approval
Deliver SSLKey | bar: 2026 W28 to 2026 W29
|  | Submit Design Assessment | 2026 W37: Start; 2026 W43: Submit; 2026 W50: Approval
|  | Submit System Testing Assessment | 2026 W37: Start; 2026 W51: Submit; 2027 W5: Approval
|  | Precertification Approval | 2027 W6: Submit; 2027 W7: Approval
|  | Testing Schedule Approval | 2027 W8: Submit; 2027 W9: Approval
Bench production(DT/HDCC) | bar: 2026 W1 to 2026 W9
Bench Pretest | bar: 2026 W37 to 2027 W1
Bench shipment to AA Lab | bar: 2026 W50 to 2026 W52
|  | 3PL Bench Test | 2027 W2: Round1; 2027 W5: Issue Fix; 2027 W12: Round 2
|  | InVehicleTest | 2027 W1: pre test; 2027 W12: pre test; 2027 W14: Vehicle Audit
Bench shipment to Google | bar: 2027 W9 to 2027 W12
|  | Google Final Review | 2027 W18: Approval
| Certification(2nd) | Vehicle Available | bar: 2026 W50
|  | Submit Application | 2026 W23: Submit; 2026 W32: Approval
Submit CERS
|  | Submit Project Specification | 2026 W35: Submit; 2026 W44: Approval
Deliver SSLKey | bar: 2026 W45 to 2026 W46
|  | Submit Design Assessment | 2026 W51: Start; 2027 W7: Submit; 2027 W14: Approval
|  | Submit System Testing Assessment | 2026 W51: Start; 2027 W15: Submit; 2027 W22: Approval
|  | Precertification Approval | 2027 W23: Submit; 2027 W24: Approval
|  | Testing Schedule Approval | 2027 W25: Submit; 2027 W26: Approval
Bench production(Promaster/Fastback/Toro) | bar: 2026 W14 to 2026 W33
Bench Pretest | bar: 2026 W51 to 2027 W15
Bench shipment to AA Lab | bar: 2027 W17 to 2027 W19
|  | 3PL Bench Test | 2027 W22: Round1; 2027 W25: Issue Fix; 2027 W30: Round 2
|  | InVehicleTest | 2026 W51: pretest; 2027 W30: pre test; 2027 W32: Vehicle Audit
Bench shipment to Google | bar: 2027 W27 to 2027 W30
|  | Google Final Review | 2027 W36: Approval

## Test Vehicle Usage Plan
Year |  |  | 2026 | [18 empty] | 2027
Week |  |  | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37
Date |  |  | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2027-09-13
Project Milestone
| Vehicle | Vehicle Available | 2026 W35: 1st; 2026 W51: 2nd
CarPlay | Certification(1st) | ITUT & siri&esiri | bar: 2026 W45 to 2026 W52
|  | Location Test & Wireless Performance | 2026 W49: pre test + Issue Fix; 2027 W1: Audit
|  | Vehicle Assessment | 2027 W9: Round 1; 2027 W11: Issue Fix; 2027 W14: Round 2
| Certification(2nd) | ITUT & siri&esiri | bar: 2026 W51 to 2027 W6
|  | Vehicle Assessment | 2027 W27: Round 1; 2027 W29: Issue Fix; 2027 W32: Round 2
Android Auto | Certification(1st) | InVehicleTest | 2026 W49: pre test + Issue Fix; 2027 W8: pre test; 2027 W10: Vehicle Audit
| Certification(2nd) | InVehicleTest | 2026 W51: pretest + Issue Fix; 2027 W30: pre test; 2027 W32: Vehicle Audit

## chang log
|  | 修改前 | 修改后
全功能节点 |  | 2026-08-10 | 2026-08-10
CarPlay 1st | Bench Pretest | W33-W49 17周 | W37-W53 17周
| Bench shipment to CarPlay lab | W47·W48 2周 | W51·W52 2周
| AuditTest | W50·2027W4 8周 | 2027W1·2027W8 8周
| Vehicle Assessment | 2027W5·2027W11 7周 | 2027W9·2027W15 7周
| Exception Request | 2027W12·2027W13 2周 | 2027W16·2027W17 2周
| ITUT & siri&esiri | W38·W46 9周 | W41·W48 8周
| Location Test & Wireless Performance | W47·2027W4 11周 | W49·2027W6 11周
| Apple Final Review | 2027W14 1周 | 2027W18 1周
Android Auto 1st | Submit Design Assessment | W33·W46 14周 | W37·W50 14周
| Submit System Testing Assessment | W33·27W1 22周 | W37·27W5 22周
| Precertification Approval | 27W2·27W3 2周 | 27W6·27W7 2周
| Testing Schedule Approval | 27W4·27W5 2周 | 27W8·27W9 2周
| Bench Pretest | W33·W50 18周 | W37·27W1 18周
| Bench shipment to AA Lab | W46·W48 3周 | W50·W52 3周
| 3PL Bench Test | W51·27W10 13周 | 27W2·27W14 13周
| InVehicleTest | Phase 1 W47·27W2 9周 Phase 2 27W8·27W10 3周 | Phase 1 W49·27W4 9周 Phase 2 27W12·27W14 3周
| Bench shipment to Google | 27W5·27W8 4周 | 27W9·27W12 4周
| Google Final Review | 27W11·27W14 4周 | 27W15·27W18 4周